## How Governance Works
Communications V2 — Package Tracker & Governance
Cowork-owned. Claude builds packages; Cowork tracks status, reviews outputs, updates backlog + QA.
Ownership | Claude owns implementation (builds packages). Cowork owns governance (status, output review, backlog + QA updates).
The loop | For each package: Claude builds → tests → commits → returns a Package Report. Cowork applies the Review Gate, updates the Package Tracker, marks mapped backlog tasks + QA cases, then releases the next package.
Tabs
Package Tracker | Live status of PKG-01..20. Cowork updates Status / Review / dates / commit / blockers.
Package > Backlog map | Which backlog task IDs each package satisfies (Cowork marks them Done as packages land).
Package > QA map | Which QA test IDs each package enables; PKG-18 runs the full matrix on Resend + Twilio.
Escalation Log | The ONLY five triggers: doctrine, security, compliance, external credential, destructive migration.
Review Gate | Checklist Cowork applies to every Package Report before accepting it.
Escalation rule | Claude escalates ONLY for: doctrine conflict, security concern, compliance concern, external credential requirement, destructive migration. Everything else: reasonable repo-grounded decision, documented in the report.
Status values | Not started · Ready · In progress · In review · Accepted · Blocked
Review values | Pending · Approved · Changes requested

## Package Tracker
Package Tracker
PKG-01 → 18 (V1) · PKG-19 → 20 (V1.5). Cowork maintains Status / Review / dates / commit / blockers.
PKG | Package | Phase | Depends | Status | Review | Started | Completed | Commit / branch | Blockers / notes
PKG-01 | Foundation: flags, guardrail tests, telemetry | P0 | — | Ready | Pending
PKG-02 | Conversation core schema + audit | P2 | 01 | Not started | Pending
PKG-03 | Delivery events + receipts | P2/P1 | 02 | Not started | Pending
PKG-04 | Recipients + preferences + audit | P2 | 02 | Not started | Pending
PKG-05 | Templates + announcements schema | P2 | 02 | Not started | Pending
PKG-06 | Provider abstraction (Resend/Twilio) | P1 | 01 | Not started | Pending
PKG-07 | Inbound pipeline (email + reply) | P1 | 03,06 | Not started | Pending
PKG-08 | Preferences & compliance engine | P8 | 04,06 | Not started | Pending
PKG-09 | Communication Health service + API | P2 | 03,04,08 | Not started | Pending
PKG-10 | Assignment & SLA service | P9 | 02 | Not started | Pending
PKG-11 | Command Center shell | P3 | 09,10 | Not started | Pending
PKG-12 | Composer V2 (consent-gated) | P5 | 06,08,11 | Not started | Pending
PKG-13 | Record Communications tab | P4 | 09,12 | Not started | Pending
PKG-14 | Templates (visual-first) | P6 | 05,12 | Not started | Pending
PKG-15 | Announcements (operator-first) | P7 | 05,08,14 | Not started | Pending
PKG-16 | Deliverability dashboard | P10 | 03,06 | Not started | Pending
PKG-17 | BOS communication intelligence | P11 | 11,13 | Not started | Pending
PKG-18 | QA hardening (Resend + Twilio) | P12 | ALL | Not started | Pending
PKG-19 | V1.5 — Google Workspace adapter | P1.5 | 06 | Deferred | Pending
PKG-20 | V1.5 — Microsoft 365 adapter | P1.5 | 06 | Deferred | Pending

## Package - Backlog map
Package → Backlog map
Cowork marks these backlog task IDs Done as each package is Accepted.
PKG | Package | Backlog task IDs (in Sprint Backlog workbook) | Mark Done?
PKG-01 | Foundation | 0.10, 0.11, 0.12 (doctrine specs 0.1–0.9 ratified by the Freeze)
PKG-02 | Conversation core schema | 2.1, 2.8
PKG-03 | Delivery events + receipts | 2.2, 1.8
PKG-04 | Recipients + preferences | 2.5, 2.9 (recipients), 2.10/2.11 partial
PKG-05 | Templates + announcements schema | 2.6, 2.7
PKG-06 | Provider abstraction | 1.1, 1.2, 1.5, 1.6, 1.9, 1.10, 1.11
PKG-07 | Inbound pipeline | 1.7
PKG-08 | Preferences & compliance | 0.7, 8.1, 8.2, 8.3, 8.4, 8.5, 8.6, 8.7
PKG-09 | Communication Health | 0.3, 2.3
PKG-10 | Assignment & SLA | 9.1, 9.2, 9.3, 9.4, 9.5, 9.6
PKG-11 | Command Center shell | 3.1, 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.10, 3.11, 3.12
PKG-12 | Composer V2 | 3.6, 5.1, 5.2, 5.3, 5.5, 5.6, 5.7, 5.8, 5.9, 5.10, 5.11
PKG-13 | Record Communications tab | 4.1, 4.2, 4.3, 4.4, 4.5, 4.6, 4.7, 4.8, 4.9, 4.10, 4.11
PKG-14 | Templates | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7, 6.8
PKG-15 | Announcements | 7.1, 7.2, 7.3, 7.4, 7.5, 7.6, 7.7
PKG-16 | Deliverability | 10.1, 10.2, 10.3, 10.4, 10.5, 10.6, 10.7
PKG-17 | BOS intelligence | 5.4, 11.1, 11.2, 11.3, 11.4, 11.5, 11.6, 11.7, 11.8, 11.9, 11.10
PKG-18 | QA hardening | 12.1, 12.2, 12.3, 12.4, 12.5, 12.6, 12.7, 12.8, 12.9, 12.10
PKG-19 | V1.5 Google | 1.4
PKG-20 | V1.5 Microsoft | 1.3

## Package - QA map
Package → QA map
Cases each package enables. PKG-18 executes the full matrix on Resend + Twilio.
PKG | Package | QA test IDs (in QA workbook) | Run at
PKG-03 | Delivery events + receipts | E-05, E-06 | PKG-18
PKG-06 | Provider abstraction | E-01, E-02, S-01 | PKG-18
PKG-07 | Inbound pipeline | E-03, E-04, S-02 | PKG-18
PKG-08 | Preferences & compliance | E-07, S-03, S-04, S-05, CP-01..CP-06 | PKG-18
PKG-10 | Assignment & SLA | CC-01, CC-02, CC-05 | PKG-18
PKG-11 | Command Center shell | CC-03, CC-04, CC-06, CC-07, CC-08, PF-01, PF-02, PF-05 | PKG-18
PKG-12 | Composer V2 | S-06 (gating), E-01/E-02 via composer | PKG-18
PKG-13 | Record Communications tab | CT-01..CT-06, PF-03 | PKG-18
PKG-14 | Templates | TM-01..TM-05 | PKG-18
PKG-15 | Announcements | AN-01..AN-05 | PKG-18
PKG-16 | Deliverability | E-06 (dashboard view) | PKG-18
PKG-17 | BOS intelligence | BO-01..BO-05, PF-04 | PKG-18
PKG-18 | QA hardening | ALL areas, full sign-off | PKG-18

## Escalation Log
Escalation Log
The ONLY five triggers. Anything else: Claude decides + documents in the package report.
# | Date | Package | Trigger type | Description | Decision / resolution | Resolved?
Allowed triggers: (1) doctrine conflict (2) security concern (3) compliance concern (4) external credential requirement (5) destructive migration risk
1
2
3
4
5
6
7
8
9
10
11
12

## Review Gate
Per-Package Review Gate
Cowork applies this to every Package Report before marking the package Accepted.
# | Gate check | Pass?
1 | Acceptance criteria in the package work order are all met.
2 | Relevant Doctrine Guardrails (Backlog workbook) all Pass for the touched surfaces.
3 | Tests written + green: `cd web && npm run test` (and named suites for the package).
4 | Lint clean: `npm run lint`. Build/types pass: `npm run build` (includes verify:module-imports).
5 | Server-only safety: no client import of server/secret modules; no window/localStorage in server paths (PRE_COMMIT_SHIP_CHECK pattern).
6 | No provider-specific branching escaped the adapter layer (provider contract test green).
7 | RLS + org/location scope enforced on any new data access; no cross-tenant leak.
8 | Migrations additive + reversible; NO destructive change in place (else escalate).
9 | No auto-send path introduced; BOS remains review-first; BOS not embedded in content.
10 | Performance doctrine: no blank shells, single reveal, drawer + BOS rail maintained (UI packages).
11 | Audit rows written for any consent/assignment/SLA state change.
12 | Docs updated: docs/product/communications.md (+ relevant sprint doc).
13 | Package Report complete: summary, decisions made, files changed, tests, commit, mapped backlog + QA IDs.
14 | Mapped backlog task IDs marked Done; mapped QA IDs noted as enabled.