## README
Alloy Communications V2 — Command Center Sprint
Management workbook · backlog, roadmap, prerequisites, doctrine guardrails, definition of done
Mission | Transform Messaging into a full Communications Command Center while preserving every existing Alloy doctrine: Workspace, Work Units, Drawers, BOS, Actions. Communications are operational work. Families and relationships are the primary object. Messages are supporting artifacts.
Must not resemble | Gmail, Outlook, HubSpot, Salesforce, Mailchimp, Front, Intercom, or Twilio Console.
Built on (existing) | Canonical communication_* tables (threads, messages, reads, provider_bindings); executeCommunicationsSend canonical send path; AdminV2 shell + BOS command rail; Bend Pine light surfaces; drawer doctrine (Communications is already a fixed core tab). New work extends these — it does not expand legacy `messages`.
Tabs in this workbook
Roadmap | Phase 0–12 sequencing: objective, key deliverables, dependencies, external prerequisites, exit criteria, status.
Backlog | Full task breakdown across all 13 phases. Each row has acceptance criteria, type, priority, estimate, dependencies, owner, status.
Prerequisites | External, non-engineering prerequisites (Google, Microsoft, Twilio, domains, legal). Tracked but NON-BLOCKING for engineering.
Doctrine Guardrails | The locked UX doctrine as a verifiable pass/fail checklist. Review every phase against it.
Definition of Done | Working agreement, per-task DoD, and the operating rules for running this sprint with minimal intervention.
How to use | Work top-down by phase. Engineering proceeds on the canonical path without waiting on prerequisites; provider-gated tasks are flagged in Backlog and Prerequisites. A task is Done only when its acceptance criteria and the Definition of Done both pass. Communications V2 is complete only after the QA workbook passes.
Estimate key | Points (Fibonacci): 1≈≤half day · 2≈1 day · 3≈2–3 days · 5≈~1 week · 8≈~2 weeks. T-shirt in parentheses where useful.
Status values | Not started · In progress · Blocked · In review · Done
Owner | Fill with the responsible engineer/lead. Left blank by design — assign during sprint planning.

## Roadmap
Phase Roadmap
Implementation order — each phase ships operator-visible value on the canonical path
Phase | Objective | Key deliverables | Depends on | External prereqs | Exit criteria | Status
Phase 0 — Foundation & Doctrine Lock | Lock doctrine, data model, and contracts before code. | Signed doctrine + guardrail tests; data-model decision; health/preferences/timeline/provider/compliance/assignment/BOS contracts; flag + rollout plan. | — | Legal review (defaults) | All contracts ratified; guardrail test harness green; no scope ambiguity. | Not started
Phase 1 — Provider Layer | Channel-agnostic provider abstraction. | Send/receive/status abstraction; Resend, M365, Google, Twilio adapters; inbound + webhook normalization; failover. | P0 | Google OAuth · Azure app · Twilio/10DLC | Resend conforms to abstraction; no provider leakage in app layer; contract tests green. | Not started
Phase 2 — Unified Communication Model | Canonical schema for everything downstream. | Thread/message lifecycle + read receipts; health denorm; unified timeline; preferences; templates; announcements; assignment/SLA; RLS. | P0, P1 | — | Migrations applied + backfilled; RLS verified; timeline contract satisfied. | Not started
Phase 3 — Command Center UI | Global three-column command surface. | Queue → Conversation Workspace → BOS rail; operational queues; filters/search; metrics strip; assignment controls; single-reveal perf. | P2 | — | Three-column shell live; operational queues (not folders); BOS rail reused; no blank shells. | Not started
Phase 4 — Record Communications Tabs | Relationship-level communication context. | Communications tab on Lead/Person/Child: timeline, health, consent, quick reply, notes. Shared thread view extraction. | P2, P3 | — | Tabs live on 3 drawers; no inbox/assignment/deliverability/bulk tools in record tabs. | Not started
Phase 5 — Composer V2 | Single unified composer. | Email/SMS/Internal Note; attachments; templates; variables; BOS drafting; send later; drafts; desktop+mobile preview. | P2, P3 | — | One composer in Command Center + record tabs + Quick Message; channel/consent gating correct. | Not started
Phase 6 — Templates | Visual-first reusable templates. | Visual builder (not token-first); desktop+mobile preview; variables; categories; approval status; snippets; versioning. | P2, P5 | — | Templates render with variables; approval status enforced; no broken tokens. | Not started
Phase 7 — Announcements | Operator-first broadcasts via Action Workspace. | Builder on Action Workspace doctrine; targeting; multi-channel delivery; tracking; closure/holiday/re-enrollment/tuition/program templates. | P2, P5, P6 | — | Targeted send delivers + tracks; compliance classification applied; not a campaign tool. | Not started
Phase 8 — Communication Preferences | Platform-wide per-person consent. | Per-person categories (email/SMS transactional+marketing, announcements, emergency); source/timestamp/method/user audit; send-time enforcement. | P2 | Legal review (defaults) | Opt-in/opt-out enforced at send; full audit trail; STOP/START/HELP wired. | Not started
Phase 9 — Assignment & SLA | Conversation ownership + service levels. | Assigned user/team/unassigned; claim/reassign/route; SLA timers (first response, overdue, stale); SLA-at-risk surfacing. | P2, P3 | — | Claim/reassign/route work; SLA timers fire; at-risk visible in queue + metrics. | Not started
Phase 10 — Deliverability | Admin monitoring + reputation. | Dashboard: failures, bounce, unsubscribe, spam, domain verification (SPF/DKIM/DMARC), sender reputation, carrier (10DLC) status; alerting. | P1, P2 | Domains · Twilio/10DLC | Dashboard reflects real provider signals; alerts fire on thresholds. | Not started
Phase 11 — BOS Intelligence | Communication intelligence in the BOS rail. | Summary; recommended response; suggested follow-up; task + enrollment recs; missing-info; risk; read-receipt analysis; response likelihood. | P2, P3 | — | BOS rail surfaces all required intelligences; review-first; no auto-send. | Not started
Phase 12 — QA Hardening | Exit-criteria verification. | Email/SMS/Tabs/Command Center/Templates/Announcements/Compliance/BOS/Performance QA; complete QA workbook + sign-off. | All | All prereqs live for full QA | Every QA exit criterion passes; sign-off recorded. Only then is V2 complete. | Not started

## Backlog
Sprint Backlog
All phases · acceptance-criteria driven · dependencies by task ID
ID | Phase | Epic | Task | Acceptance criteria | Type | Pri | Est | Depends on | Owner | Status
0.1 | P0 Foundation | Doctrine | Ratify locked UX doctrine + guardrails | Signed doctrine: three-column Command Center; families as primary object; messages as artifacts; explicit non-resemblance list. Stored in docs/sprints. | Spec | P0 | 2
0.2 | P0 Foundation | Data model | Lock canonical model decision | Decision recorded: extend communication_* tables; no new columns/events on legacy `messages`. Migration policy approved. | Spec | P0 | 2 | 0.1
0.3 | P0 Foundation | Contracts | Communication Health object contract | First-class object defined: Last Contact, Last Read, Unread, Response Rate, Engagement Score, Channel Preference, Consent Status. Computation rules specified. | Spec | P0 | 3 | 0.2
0.4 | P0 Foundation | Contracts | Communication Preferences model contract | Per-person (not per-lead/conversation) categories defined with audit fields (source, timestamp, method, user). | Spec | P0 | 3 | 0.2
0.5 | P0 Foundation | Contracts | Unified Timeline event contract | Single event model covers Email, SMS, Call, Internal Note, Announcement; extensible to Portal/WhatsApp/Voice. Chronological + filterable. | Spec | P0 | 3 | 0.2
0.6 | P0 Foundation | Contracts | Provider abstraction interface contract | send/receive/status interface; zero provider-specific assumptions in application layer. Reviewed against architecture doc. | Spec | P0 | 3 | 0.2
0.7 | P0 Foundation | Contracts | Compliance doctrine contract | Lead→Marketing, Enrolled→Transactional; promotional override always available when appropriate; default to safer class; platform-owned (not tenant-configurable). | Spec | P0 | 3 | 0.1
0.8 | P0 Foundation | Contracts | Assignment & SLA model contract | assigned user/team/unassigned; claim/reassign/route; SLA timers (first response, overdue, stale) defined. | Spec | P0 | 3 | 0.2
0.9 | P0 Foundation | Contracts | BOS intelligence capability contract | Defines summary, recommended response, follow-up, task/enrollment recs, missing-info, risk, read-receipt analysis, response likelihood. Review-first; no auto-send. | Spec | P0 | 3 | 0.2
0.10 | P0 Foundation | Rollout | Feature-flag + rollout gate plan | Flags per phase; staged rollout; rollback path; dual-write strategy where needed. | Spec | P1 | 2 | 0.2
0.11 | P0 Foundation | Telemetry | Analytics/telemetry event plan | Events for health metrics + deliverability defined; instrumentation plan approved. | Spec | P1 | 2 | 0.3
0.12 | P0 Foundation | Guardrails | Doctrine guardrail test harness | Automated contract/lint tests fail any regression toward email-folders, generic inbox, or BOS-in-content. Wired to CI. | Test | P0 | 5 | 0.1
1.1 | P1 Provider | Abstraction | Provider abstraction interface | Channel-agnostic send/receive/status implemented; app layer references abstraction only. | Build | P0 | 5 | 0.6
1.2 | P1 Provider | Email | Resend adapter conformance | Current Resend path refactored behind abstraction; parity with existing send + webhooks. | Build | P0 | 3 | 1.1
1.3 | P1 Provider | Email | Microsoft 365 (Graph) adapter | Send/receive via Graph behind abstraction. GATED on Azure app registration + prod permissions. | Build | P1 | 8 | 1.1
1.4 | P1 Provider | Email | Google Workspace (Gmail) adapter | Send/receive via Gmail API behind abstraction. GATED on Google OAuth app + production verification. | Build | P1 | 8 | 1.1
1.5 | P1 Provider | SMS | Twilio adapter + messaging services | SMS send/receive behind abstraction. GATED on Twilio account + messaging services + 10DLC. | Build | P0 | 5 | 1.1
1.6 | P1 Provider | Bindings | Provider binding + secret_ref resolution | Bindings resolved on worker; no client-side secrets; PATCH never leaks secrets. | Build | P0 | 3 | 1.1
1.7 | P1 Provider | Inbound | Inbound normalization pipeline | Inbound email + SMS normalize to canonical communication_messages, person-first. | Build | P0 | 5 | 1.1,2.1
1.8 | P1 Provider | Status | Delivery status normalization | Resend/Twilio webhooks map to unified lifecycle: sent, delivered, opened, clicked, replied, bounced. | Build | P0 | 5 | 1.1,2.2
1.9 | P1 Provider | Health | Provider credential/health surface | Per-org provider status (connected, degraded, expired) exposed to admin. | Build | P1 | 3 | 1.6
1.10 | P1 Provider | Resilience | Failover, retries, degradation | Retry/backoff + graceful degradation when a provider is down; no lost messages. | Build | P1 | 5 | 1.1
1.11 | P1 Provider | Tests | Provider abstraction contract tests | Tests assert no provider-specific branching escapes the adapter layer. | Test | P0 | 3 | 1.1
2.1 | P2 Model | Schema | Threads: assignment + SLA + status fields | communication_threads extended (owner_user, team, assignment_state, sla_* timers, last_read, status). Migration + RLS. | Build | P0 | 5 | 0.3,0.8
2.2 | P2 Model | Schema | Messages: lifecycle + read receipts | communication_messages lifecycle (sent/delivered/opened/clicked/replied) + read-receipt fields; reads table extended. | Build | P0 | 5 | 0.3
2.3 | P2 Model | Schema | Health denormalization view | Thread/health view computes Last Contact, Last Read, Unread, Response Rate, Engagement Score, Channel Preference, Consent Status. | Build | P0 | 5 | 2.1,2.2
2.4 | P2 Model | Schema | Unified timeline event model | Timeline stores Email, SMS, Call, Internal Note, Announcement; extensible. Chronological + filter indexes. | Build | P0 | 5 | 0.5
2.5 | P2 Model | Schema | Communication preferences table | Per-person preferences with categories + audit (source, timestamp, method, user). RLS. | Build | P0 | 5 | 0.4
2.6 | P2 Model | Schema | Templates + snippets + approval | Tables for templates, reusable snippets, categories, approval status, versioning. | Build | P1 | 3 | 0.5
2.7 | P2 Model | Schema | Announcements tables | Announcement, targeting/audience, delivery, tracking tables. | Build | P1 | 3 | 0.5
2.8 | P2 Model | Schema | Assignment / SLA tracking tables | Assignment audit + SLA event tracking persisted. | Build | P1 | 3 | 0.8
2.9 | P2 Model | Schema | Internal notes as first-class type | Internal notes modeled as a message/timeline type, never sent to families. | Build | P0 | 3 | 2.4
2.10 | P2 Model | Migration | Migrations + backfill | Forward migrations + backfill from existing rows; reversible; zero data loss verified. | Build | P0 | 5 | 2.1,2.2,2.3,2.4,2.5
2.11 | P2 Model | Entity | Anchor threads to Family/primary object | Threads resolve to Family/relationship as primary object, person-first recipients. | Build | P0 | 3 | 2.1
2.12 | P2 Model | Security | RLS + org/location scope | All new tables enforce org + CRM location scope; no cross-location leakage. | Build | P0 | 5 | 2.10
3.1 | P3 Command Center | Shell | Three-column command shell | Queue → Conversation Workspace → BOS rail using AdminV2 shell + existing BOS rail doctrine. BOS not embedded in content. | Build | P0 | 8 | 2.3
3.2 | P3 Command Center | Queue | Operational work queues | Queues are operational work (Awaiting Parent Reply, Needs Follow-Up, Documents Missing, Re-enrollment Outreach, Waitlist Update) — not email folders. | Build | P0 | 8 | 3.1
3.3 | P3 Command Center | Queue | Filters, sort, search | Channel/Status/Owner/Location filters + sort + search over conversations. | Build | P0 | 5 | 3.2
3.4 | P3 Command Center | Workspace | Conversation workspace header | Family summary, lead status, program, location, owner, communication health rendered. | Build | P0 | 5 | 3.1,2.3
3.5 | P3 Command Center | Workspace | Unified conversation timeline | Chronological + filterable timeline of all channels in workspace. | Build | P0 | 5 | 3.4,2.4
3.6 | P3 Command Center | Workspace | Composer mount | Unified composer mounts in workspace (delegates to Phase 5 component). | Build | P0 | 3 | 3.5,5.1
3.7 | P3 Command Center | BOS | BOS rail mount | Existing BOS command rail mounted; reuses architecture; not embedded in message content. | Build | P0 | 3 | 3.1
3.8 | P3 Command Center | Metrics | Command Center metrics strip | New Conversations, Requires Response, SLA At Risk, Messages Sent, Response Rate with deltas. | Build | P1 | 3 | 3.2,2.3
3.9 | P3 Command Center | Perf | Single-reveal performance | No blank shells; single reveal; warm-load cache; drawer doctrine maintained. | Build | P0 | 5 | 3.1
3.10 | P3 Command Center | Assignment | Assignment controls (queue + workspace) | Claim / assign / reassign from queue and workspace (delegates to Phase 9 model). | Build | P1 | 3 | 3.2,9.1
3.11 | P3 Command Center | States | Empty/loading/error states | All states follow drawer doctrine; no flash-of-empty. | Build | P1 | 2 | 3.9
3.12 | P3 Command Center | Nav | Navigation entry + deep links | Communications nav entry; drawers deep-link into Command Center with entity filter. | Build | P1 | 2 | 3.2
4.1 | P4 Record Tabs | Lead | Communications tab — Lead drawer | Timeline, communication health, consent status, quick reply, internal notes. No inbox/assignment/deliverability/bulk tools. | Build | P0 | 5 | 4.4
4.2 | P4 Record Tabs | Person | Communications tab — Person drawer | Same record-level contract as Lead, person-scoped. | Build | P0 | 3 | 4.4
4.3 | P4 Record Tabs | Child | Communications tab — Child drawer | Same record-level contract, child-scoped. | Build | P0 | 3 | 4.4
4.4 | P4 Record Tabs | Shared | Extract shared thread view/list | CommunicationsThreadView/ThreadList shared by Command Center + record tabs (single source). | Build | P0 | 5 | 3.5
4.5 | P4 Record Tabs | Receipts | Read receipts in record context | Sent/Delivered/Opened/Clicked/Replied shown per message in record tab. | Build | P1 | 3 | 4.4,2.2
4.6 | P4 Record Tabs | Health | Communication health widget | Record-level health summary widget (reuses health object). | Build | P1 | 3 | 4.4,2.3
4.7 | P4 Record Tabs | Consent | Consent status display | Consent surfaced with link to preferences (read-only in tab). | Build | P1 | 2 | 4.4,8.1
4.8 | P4 Record Tabs | Reply | Quick reply composer | Record-scoped quick reply via unified composer. | Build | P1 | 2 | 4.4,5.1
4.9 | P4 Record Tabs | Notes | Internal notes in record tab | Add/view internal notes inline; never delivered to families. | Build | P1 | 2 | 4.4,2.9
4.10 | P4 Record Tabs | Guardrail | Record-tab scope guardrail test | Test asserts no inbox/assignment/deliverability/bulk surfaces leak into record tabs. | Test | P0 | 2 | 4.1,4.2,4.3
4.11 | P4 Record Tabs | Future | Future-entity drawer readiness | Additive-tab pattern documented + componentized for future drawers. | Spec | P2 | 2 | 4.4
5.1 | P5 Composer | Core | Single unified composer | One component supports Email, SMS, Internal Note; used everywhere. | Build | P0 | 8 | 2.2,2.9
5.2 | P5 Composer | Attach | Attachments | Attach files via documents pipeline; size/type validated. | Build | P1 | 3 | 5.1
5.3 | P5 Composer | Templates | Template insertion + variables | Insert template; variables resolve against record context. | Build | P1 | 3 | 5.1,6.3
5.4 | P5 Composer | BOS | BOS-assisted drafting | BOS draft entry point returns editable draft per channel; review-first. | Build | P1 | 5 | 5.1,11.2
5.5 | P5 Composer | Schedule | Send later / scheduling | Schedule send via scheduled-sends path; person + entity resolved. | Build | P1 | 3 | 5.1
5.6 | P5 Composer | Drafts | Drafts save/resume | Draft persists and reopens with full state. | Build | P1 | 3 | 5.1
5.7 | P5 Composer | Preview | Desktop + mobile preview | Composer renders desktop and mobile previews before send. | Build | P1 | 3 | 5.1
5.8 | P5 Composer | Gating | Channel + consent gating | SMS disabled without binding/phone; sends respect consent (Phase 8). | Build | P0 | 3 | 5.1,8.4
5.9 | P5 Composer | Multi | Multi-recipient send | N recipients enqueue N canonical messages; per-recipient consent respected. | Build | P1 | 3 | 5.1,5.8
5.10 | P5 Composer | Merge | Merge Quick Message into composer | Quick Message modal uses the unified composer; no forked path. | Build | P1 | 3 | 5.1
5.11 | P5 Composer | A11y | Accessibility + keyboard | Composer fully keyboard-operable; meets a11y baseline. | Build | P2 | 2 | 5.1
6.1 | P6 Templates | Builder | Visual-first template builder | Build templates visually (not token-first); WYSIWYG editing. | Build | P1 | 8 | 2.6
6.2 | P6 Templates | Preview | Desktop + mobile preview | Template preview both viewports with sample data. | Build | P1 | 3 | 6.1
6.3 | P6 Templates | Variables | Variables / merge fields + rendering | Variable catalog; render engine resolves against record; missing-var handling. | Build | P0 | 5 | 6.1
6.4 | P6 Templates | Categories | Template categories | Templates organized by category; filterable. | Build | P2 | 2 | 6.1
6.5 | P6 Templates | Approval | Approval status workflow | Draft → pending → approved; only approved templates sendable where required. | Build | P1 | 3 | 6.1
6.6 | P6 Templates | Snippets | Reusable snippets | Snippet library insertable into templates/composer. | Build | P2 | 3 | 6.1
6.7 | P6 Templates | Version | Template versioning | Versions tracked; revert supported. | Build | P2 | 3 | 6.1
6.8 | P6 Templates | Tests | Render-test harness | Automated render tests: variables resolve, no broken tokens, both viewports. | Test | P1 | 3 | 6.3
7.1 | P7 Announcements | Builder | Announcement builder (Action Workspace) | Built on Action Workspace doctrine; operator-first, not campaign-first; not a Mailchimp clone. | Build | P1 | 8 | 2.7,5.1
7.2 | P7 Announcements | Targeting | Audience targeting | Target by segment/status/location/program; preview audience count. | Build | P1 | 5 | 7.1
7.3 | P7 Announcements | Delivery | Multi-channel delivery | Deliver via email/SMS/announcement respecting consent classification. | Build | P1 | 5 | 7.1,8.4
7.4 | P7 Announcements | Tracking | Delivery + engagement tracking | Track delivery, open, click per announcement. | Build | P1 | 3 | 7.3,2.2
7.5 | P7 Announcements | Templates | Operator announcement templates | Ship School Closure, Holiday Reminder, Re-enrollment, Tuition Update, Program Announcement. | Build | P2 | 3 | 7.1,6.1
7.6 | P7 Announcements | Compliance | Classification gating | Emergency vs marketing classification applied; override path audited. | Build | P0 | 3 | 7.3,0.7
7.7 | P7 Announcements | Schedule | Scheduling + review/approval | Schedule + require review before broadcast. | Build | P2 | 3 | 7.1
8.1 | P8 Preferences | UI/API | Per-person preferences UI + API | Manage preferences per person; reads/writes audited. | Build | P0 | 5 | 2.5
8.2 | P8 Preferences | Categories | Preference categories | Email (transactional/marketing), SMS (transactional/marketing), Announcements, Emergency Alerts. | Build | P0 | 3 | 8.1
8.3 | P8 Preferences | Audit | Source/timestamp/method/user audit | Every change records source, timestamp, method, user; immutable audit trail. | Build | P0 | 3 | 8.1
8.4 | P8 Preferences | Enforce | Consent enforcement at send | Send pipeline blocks/permits by category + lifecycle class; safer default on ambiguity. | Build | P0 | 5 | 8.2,0.7
8.5 | P8 Preferences | Optout | Opt-out surfaces in messages | Unsubscribe/preference links in email; reflected back to preferences. | Build | P1 | 3 | 8.1
8.6 | P8 Preferences | SMS | STOP/START/HELP handling | Inbound SMS keywords update preferences + send compliant auto-responses. | Build | P0 | 3 | 8.1,1.7
8.7 | P8 Preferences | Surface | Preferences in tabs + health | Consent status surfaced in record tabs + Command Center health. | Build | P1 | 2 | 8.1,2.3
9.1 | P9 Assignment | Ownership | Ownership model | assigned user / assigned team / unassigned states on conversations. | Build | P0 | 3 | 2.8
9.2 | P9 Assignment | Routing | Claim / reassign / queue routing | Operators claim, reassign; routing rules place into queues. | Build | P1 | 5 | 9.1
9.3 | P9 Assignment | SLA | SLA timers | first response, overdue response, stale conversation timers compute correctly. | Build | P1 | 5 | 9.1,2.8
9.4 | P9 Assignment | Surface | SLA-at-risk surfacing | At-risk conversations surface in queue + metrics strip. | Build | P1 | 3 | 9.3,3.8
9.5 | P9 Assignment | Rules | Routing rules config | Admin-config routing rules (operator-owned, bounded). | Build | P2 | 3 | 9.2
9.6 | P9 Assignment | Audit | Assignment audit + notifications | Assignment changes audited; assignee notified. | Build | P2 | 3 | 9.1
10.1 | P10 Deliverability | Dashboard | Deliverability dashboard | Admin dashboard aggregates provider signals. | Build | P1 | 5 | 1.8
10.2 | P10 Deliverability | Failures | Failures + bounce rates | Delivery failures and bounce rates tracked + displayed. | Build | P1 | 3 | 10.1
10.3 | P10 Deliverability | Complaints | Unsubscribe + spam complaints | Unsubscribe and spam-complaint rates tracked. | Build | P1 | 3 | 10.1,8.5
10.4 | P10 Deliverability | Domains | Domain verification status | SPF/DKIM/DMARC status per customer domain shown. GATED on customer DNS. | Build | P1 | 3 | 10.1
10.5 | P10 Deliverability | Reputation | Sender reputation | Sender reputation signal surfaced. | Build | P2 | 3 | 10.1
10.6 | P10 Deliverability | Carrier | Carrier (10DLC) registration status | 10DLC registration status shown. GATED on Twilio registration. | Build | P1 | 3 | 10.1
10.7 | P10 Deliverability | Alerts | Threshold alerting | Alerts fire when bounce/spam/failure exceed thresholds. | Build | P2 | 3 | 10.2,10.3
11.1 | P11 BOS | Summary | Conversation summary | BOS rail summarizes a conversation accurately + concisely. | Build | P1 | 5 | 3.7,2.4
11.2 | P11 BOS | Response | Recommended response | BOS proposes a customer-facing response per channel; review-first; no auto-send. | Build | P1 | 5 | 11.1
11.3 | P11 BOS | Followup | Suggested follow-up | BOS suggests follow-up actions/timing. | Build | P1 | 3 | 11.1
11.4 | P11 BOS | Tasks | Task recommendations | BOS recommends operational tasks from conversation. | Build | P1 | 3 | 11.1
11.5 | P11 BOS | Enroll | Enrollment recommendations | BOS surfaces enrollment-advancing recommendations. | Build | P2 | 3 | 11.1
11.6 | P11 BOS | Missing | Missing-information detection | BOS flags missing info needed to advance the family. | Build | P1 | 3 | 11.1
11.7 | P11 BOS | Risk | Communication risk detection | BOS flags at-risk conversations (silence, negative signal, SLA breach). | Build | P1 | 3 | 11.1,9.3
11.8 | P11 BOS | Receipts | Read-receipt analysis | BOS interprets read-receipt signals (opened-not-replied, etc.). | Build | P2 | 3 | 11.1,2.2
11.9 | P11 BOS | Likelihood | Response likelihood | BOS estimates likelihood of family response. | Build | P2 | 3 | 11.1
11.10 | P11 BOS | Integration | BOS rail integration | All intelligences surface in existing rail; review-first; consistent with rail doctrine. | Build | P0 | 3 | 11.1
12.1 | P12 QA | Email | Email QA pass | Send, receive, reply, read receipt, bounce handling all pass (see QA workbook). | Test | P0 | 3 | ALL
12.2 | P12 QA | SMS | SMS QA pass | Send, receive, STOP, START, HELP all pass. | Test | P0 | 3 | ALL
12.3 | P12 QA | Tabs | Communications tab QA | Lead, Person, Child tabs pass. | Test | P0 | 2 | ALL
12.4 | P12 QA | Command Center | Command Center QA | Assignment, filters, SLA, search pass. | Test | P0 | 3 | ALL
12.5 | P12 QA | Templates | Templates QA | Preview, variables, rendering pass. | Test | P0 | 2 | ALL
12.6 | P12 QA | Announcements | Announcements QA | Targeting, delivery, tracking pass. | Test | P0 | 2 | ALL
12.7 | P12 QA | Compliance | Compliance QA | Opt-in, opt-out, audit trail pass. | Test | P0 | 3 | ALL
12.8 | P12 QA | BOS | BOS QA | Summary, draft response, follow-up recommendations pass. | Test | P0 | 2 | ALL
12.9 | P12 QA | Perf | Performance QA | No blank shells; single reveal; drawer doctrine maintained; BOS rail maintained. | Test | P0 | 3 | ALL
12.10 | P12 QA | Signoff | QA workbook + sign-off | All exit criteria green; sign-off recorded. Only then is V2 complete. | Test | P0 | 2 | 12.1,12.2,12.3,12.4,12.5,12.6,12.7,12.8,12.9

## Prerequisites
External Prerequisites
Human/credential/compliance prerequisites — tracked but NON-BLOCKING for engineering
# | Area | Prerequisite | Owner | Blocks | Status | Notes
1 | Google | OAuth application created |  | Task 1.4 | Not started
2 | Google | Production verification approved |  | Task 1.4 (prod) | Not started
3 | Microsoft | Azure application registration |  | Task 1.3 | Not started
4 | Microsoft | Production permissions granted |  | Task 1.3 (prod) | Not started
5 | Twilio | Account ownership confirmed |  | Tasks 1.5, 8.6 | Not started
6 | Twilio | Messaging services configured |  | Task 1.5 | Not started
7 | Twilio | 10DLC registration complete |  | Tasks 1.5, 10.6, SMS QA | Not started
8 | Email Domains | SPF configured (per customer) |  | Task 10.4 | Not started | Tenant DNS responsibility
9 | Email Domains | DKIM configured (per customer) |  | Task 10.4 | Not started | Tenant DNS responsibility
10 | Email Domains | DMARC configured (per customer) |  | Task 10.4 | Not started | Tenant DNS responsibility
11 | Legal | Review compliance defaults |  | Phase 0.7 sign-off | Not started | Review + approve, no redesign
12 | Legal | Approve compliance defaults |  | Phase 8 ship gate | Not started | No redesign of doctrine
Operating rule: Do NOT block engineering progress waiting on these. Provider-gated build tasks (1.3, 1.4, 1.5) proceed against the abstraction; only their production cutover and the corresponding QA depend on these items.

## Doctrine Guardrails
Doctrine Guardrails
Locked UX doctrine as a pass/fail checklist — review EVERY phase against this
# | Guardrail (MUST / MUST NOT) | Applies to | Pass?
1 | Families/relationships are the primary object; messages are supporting artifacts. | All
2 | Communications are operational work — modeled as work, not as an inbox. | All
3 | MUST NOT resemble Gmail, Outlook, HubSpot, Salesforce, Mailchimp, Front, Intercom, or Twilio Console. | All
4 | Global surface is a three-column Command Center: Queue → Conversation Workspace → BOS rail. | Command Center
5 | Queue contains operational work (Awaiting Parent Reply, Needs Follow-Up, Documents Missing, Re-enrollment, Waitlist) — NOT email folders, generic inboxes, or chronological message lists. | Command Center
6 | Conversation Workspace shows family summary, lead status, program, location, owner, communication health, timeline, composer. | Command Center
7 | BOS uses the existing rail doctrine; BOS is NOT embedded inside communication content; existing BOS architecture reused. | Command Center / BOS
8 | Record drawers (Lead, Person, Child, future) get a Communications tab with timeline, receipts, health, consent, quick reply, notes. | Record Tabs
9 | Record tabs MUST NOT contain inbox management, assignment management, deliverability dashboards, or bulk messaging — those belong to the Command Center. | Record Tabs
10 | Communication Health is a first-class object, visible everywhere (Last Contact, Last Read, Unread, Response Rate, Engagement Score, Channel Preference, Consent Status). | All
11 | Read receipts support Sent, Delivered, Opened, Clicked, Replied. | Model / UI
12 | Communication Preferences are per person — NOT per lead, NOT per conversation. | Preferences
13 | Unified Timeline is a single chronological, filterable timeline (Email, SMS, Call, Internal Note, Announcement; future Portal/WhatsApp/Voice). | Timeline
14 | Composer is a SINGLE unified composer (Email, SMS, Internal Notes, attachments, templates, variables, BOS drafting, send later, drafts, preview). | Composer
15 | Templates are visual-first, NOT token-first (desktop + mobile preview, variables, categories, approval status, snippets). | Templates
16 | Announcements use Action Workspace doctrine — operator-first, NOT campaign-first, NOT a Mailchimp clone. | Announcements
17 | Compliance: Lead→Marketing, Enrolled→Transactional; promotional override available when appropriate; default to safer class. | Compliance
18 | Compliance controls are platform-owned, NOT tenant-configurable. | Compliance
19 | Provider abstraction required — NO provider-specific assumptions in the application layer. | Provider
20 | Performance: no blank shells; single reveal; drawer doctrine maintained; BOS rail maintained. | Performance

## Definition of Done
Definition of Done & Operating Rules
Working agreement for running this sprint with minimal intervention
Operating rules (from sponsor)
✓ | Do NOT ask for design decisions unless they conflict with this doctrine.
✓ | Do NOT ask for implementation decisions unless they require an external credential or compliance approval.
✓ | Build to completion, then return a QA workbook.
✓ | Default to the safer compliance classification whenever ambiguous.
✓ | Extend the canonical communication_* path; do not expand the legacy `messages` schema.
Per-task Definition of Done
✓ | Acceptance criteria in the Backlog row are fully met.
✓ | Doctrine Guardrails relevant to the task all Pass.
✓ | Tests written and green (unit/contract as applicable); guardrail/contract tests not weakened.
✓ | No provider-specific logic leaks into the application layer.
✓ | RLS / org + location scope enforced for any data access.
✓ | No blank shells; single reveal; drawer + BOS-rail doctrine maintained.
✓ | Telemetry events emitted where specified.
✓ | Docs updated (docs/product/communications.md + relevant sprint doc).
Per-phase exit
✓ | Every task in the phase is Done.
✓ | Phase exit criteria in the Roadmap tab are satisfied.
✓ | Guardrail review for the phase recorded as Pass.
Sprint completion (V2 complete)
✓ | All phases complete.
✓ | Every QA exit criterion in the QA workbook passes.
✓ | Sign-off recorded on the QA workbook sign-off tab.
✓ | Only after QA passes is Communications V2 considered complete.